## Revenue
Sevadari Appreciation Night – April 10, 2010
Tasks | Task assigned to | Status | Quantity | Unit Cost | Total Cost
Tickets - Revenue | All JK Captains |  | 650 | 10 | 6500
Paan - Revenue |  |  | 300 | 0.8 | 240
TOTAL REVENUE |  |  |  |  | 6740

## Expenses
Sevadari Appreciation Night – April 10, 2010
Tasks | Task assigned to | Status | Quantity | Unit Cost | Total Cost
Menu - Butter Chicken and Rice | Shelina Teja | Ordered | 600 | 3 | 1800
Menu - Naan | Shelina Teja | Ordered | 325 | 0.4 | 130
Menu - Monthar | VM Yasmin | Ordered | 675 |  | 360
Menu - Tea and Supplies | Captain Naz | Ordered |  |  | 300
Menu - Juice | Captain Naz | Ordered |  |  | 100
Menu - Cake | Captain Naz |  | 6 |  | 175
Menu - Ice-Cream cups | Yasmin Somji | Ordered | 700 | 0.5 | 350
Menu - Green Salad - Costco | VM Yasmin | Will buy on the day of | 20 | 5 | 100
Menu - Paan | VM Yasmin | Ordered | 300 | 0.7 | 210
Venue - Lions Gate JK Social Hall | Shiraz Ramji | Confirmed | 1 | 300 | 300
Band - (includes sound, air ticket and accom.) | VM Yasmin and Captain Naz | Confirmed | 1 | 1000 | 1000
Stage Decoration | VM Feroza |  | 1 | 100 | 100
TOTAL EXPENSES |  |  |  |  | 4925

## Action Items
Sevadari Appreciation Night – April 10, 2010
# | Tasks | Task assigned to | Status | Notes
1 | What is the status of Project proposal? | Shiraz | Completed
2 | What is the status of the updated Ticket? Has it been signed off by communication? Can it go print? | VM Kahir | Completed | Update 3/29/10 from VM Yasmin: Tickets has been picked up by VM Yasmin. -------------------------- Update 3/26/10 from VM Kahir: I have approved the attached ticket proofs, and I have asked them to put a rush order on them. As soon as I hear that they are ready I will pick them up and the 3 Vice Majors will distribute them to the JK's ------------------------- Notes from CC 3/24/10 : No need to worry about rushing for Thursday, we can do drive by to all JK's and deliver the tickets. ------------------------- Updated Notes: Will the tickets be ready by Thursday Noon? ------------------------ Comments by Akbar Khoja:Tickets design has been finalized and approved by Ali and Ismail Lila. Tickets has been ordered by Kahir to Westwood Printing (Shenaz)
3 | Tickets Distribution to all JK's |  |  | Update 4/5/10: Tickets has been delivered to all JK's and ticket sales are going fine. Update 3/29/10 from Major Zen: Major's will sort out the tickets on Wednesday March 31st, and will deliver to council office to send out with the JK package, Tickets and announcement will be attention to Captains, announcement will be read on Saturday April 3rd in all JK's. Major will also communicate to Captains that this event is not geared for kids so no tickets will be sold to any badged volunteer or sevadari's kids. ------------------------- Update 3/26/10 from VM Kahir: We have allocated tickets to each JK based on the proportion of sevadaris they have comparative to the aggregate number. The numbers work out as follows: Burnaby Lake: 150 IJKC: 120 HQ:96 RMD: 78 TC: 60 DT: 48 FV:36 Abbotsford: 6 Chilliwack: 6 Once we get the tickets in hand, we will circulate the attached announcement to be read in alll JK's. The tickets will be given to the Captains who will be responsible for selling and collectin money. The majors will collect the money from the Captains. Each Captain will decide on whatever strategy they are comfortable with when selling tickets. Notes from CC 3/24/10 : Major Zen, VM Kahir and VM Yasmin will take this off-line and will communicate the group with the number of tickets to be distributed to each JK's ---------------------------- Tickets – 650 total tickets to be printed – 600 will be distributed for sale and 50 will be reserved but will be sold to Jamati Mukhi/Kamadia and council members. Tickets distribution will be as follows.. Burnaby Lake -------------------- 150 tickets HQLG ------------------------------ 100 tickets Darkhana ------------------------- 75 tickets Richmond ------------------------- 75 tickets Tri-City ----------------------------- 75 tickets Downtown ------------------------- 25 tickets Fraser Valley --------------------- 50 tickets SFU/UBC -------------------------- 10 tickets Chilliwack ------------------------ 15 tickets Abbotsford ---------------------- 15 tickets TOTAL TICKETS ======== 590 tickets Remaining 60 will be distributed to JK where we see more demand
4 | Are Captains aware of the details of the Music Party? Are they aware of the marketing they need to do? | Will organize by Captain Naz | Completed | Update 3/29/10 : Captain Maa has now communicated to TC, Chilliwack and Abbotsford captains, VM Feroza will communicate to SFU M/K's to pickup their tickets from Darkhana and UBC M/K's to pick up from DT. Notes from CC 3/24/10 : Captain Maa Naz has talked with most of the JK Captains besides TC, Chilliwack and Abbotsford which she will take care. SFU/UBC is still in question and Majors are deciding on that. -------------------------- Updated Notes: Yes, Captain Maa Naz has communicated to all Captains besides SFU, UBC, Chilliwack and Abbotsford. Comments by Captain Maa Naz: I think we need to make 6 phone calls to captains and explain the event and make sure that they identify their j.k. sevadaris teams and offer tickets but put a strict time line on it eg. tickets on hand on 26th leave 40% for sevadaris and 60% for volunteers put a time limit of 10 days on each side and then offer to the other side if tickets left over.
5 | Is the program for the night decided? | VM Feroza | Completed | Update 4/5/10: VM Feroza has created a programe and not sure if we are going for any dances????? Update 3/29/10: Ayshaa and Feroza will be meeting this weekend to finalize the programe, there are two dance performences in the programe.
6 | Who are the Emcees? | VM Feroza | Completed | Updated Notes: Ayshah and VM Feroza are now confirmed as an Emcees. Comments by Captain Maa Naz: emcee was talking to feroza she is going to ask Aysha if not her I think we should consider fe and zahir (he is good with the crowds)
7 | What is the HR Plan? Who is going to and when are we going to connect with previous leadership to help with the event? | Will organize by Captain Naz | In-Process | Update 4/1/30: Captain Nick confirmed that he will look after the parking duties at the day of the event. Update 3/30/10: Shiraz Ramji will work on the Security requirements and he suggested to communicate with Captain Nick for Parking requirements. I have requested VM Yasmin to communicate to Captain Nick regarding parking requirements and she confirmed that she will get this done by April 1st. ------------------------- Update 3/29/10 : Tea/Juice and Water will be setup by Lions gate team. Setup will be done by the Lions Team (Shelina Jaffer's team) and Majors and V. Majors will be present at setup @ 2:00pm on Saturday April 10. At the event, Major's/Captain's and their spouses will help with serving the food and also will involve in take down after the event. ------------------------- Notes from CC 3/24/10 : Captain Maa will talk to Shelina (not Shelina Teja) to organize the setup at Lions gate JK on the day of the event. IVC Events team(Akbar, Shiraz and Shelina) have to organize the volunteers for Parking and security for the day of the event ------------------------- Updated Notes: All the current leadership which includes, Majors, V.Majors, Captains and their spouses will take care of the setup and take down. Comments by Captain Maa Naz: HR plan was for yasmin somji and a small team of volunteers from lions gate to set up. All captains and majors and their spouces to serve and clean up (that way the spouses dont feel lonesome and so that our newly engaged major doesnt feel like ditching us during work time) | setup time 1:00pm
8 | Who is purchasing supplies? | Captain Naz and Alnoor Bhimji | Completed | Comments by Captain Maa Naz: supplies have been ordered through Alnoor bhimji and I will go purchase the juice items.
9 | Who is inviting the leadership and M/K's? | Major's and V. Majors | Completed | Update 3/29/10 from Major: Major has already send a message to M/K's via email today. ---------------------------- Notes from CC 3/24/10 : Major Zen and VM Kahir will draft and email and send out to leadership and M/K's by tomorrow 3/25/10 ---------------------------- Comments by Captain Maa Naz: In my world mks and leadership should always be invited by the major, make some phone calls. mr major
10 | What are the times for set up and take down? | Shelina (not Teja) and Captain Naz | Completed | Update 3/29/10: Setup will start on Saturday April 10 @ 2:00pm, their will be 550 chairs, 50 people should go on bleechers and 50 will sit on carpet close to stage. VM Feroza will bring "RESERVED" signs to reserve the chairs in front for M/K's and council members. ----------------------------- Comments by Captain Maa Naz: Set up will be done at 2p.m. take down 1:30 a.m.
11 | When do we start marketing (can't happen until PP done)? |  | Completed | Comments by Captain Maa Naz: Captain Maa already talked to captains, check task# 3
12 | What are some risks that we haven't talked about? How do we mitigate them? One is that the Rays of Light Exhibition is on the April 10 and 11 in Seattle. 1500 of BC Jamat is expected to attend that exhibition. | Not a Task | Completed | Comments by Captain Maa Naz: I seriously dont think rays of light is going to be an issue if it becomes and issue we can always open up the tickets to extended members of the family of the volunteers.
13 | Who is picking up the food and delivering to HQJK? | Shelina Teja | In-Process | M/T will be assigned this task.
14 | Who is bringing the Ice-Cream Cups? | Yasmin Somji | In-Process | Update 3/29/10: Qty of the Ice-Cream cups has been updated from 650 to 700 vanilla and this will be brought in to HQLG by Yasmin Somji ------------------------------ Notes from CC 3/24/10 : Yasmin Somji will make sure that Ice-cream are delivered @ Lions Gate JK.
15 | Who is bringing the Cake? | Captain Maa Naz | Completed | Notes from 4/03/10 : Captain Maa will bring the cake to the event.
16 | Who is bringing the Monthar? | VM Kahir | Completed | Update 3/29/10: VM Kahir has increased the numbers to 675 pieces, delivery of Monthar should be @ 2:00pm so it can be placed in holders. ------------------------------ Notes from CC 3/24/10 : VM Kahir will take care of this task. ------------------------------ Have it by 2:00pm Saturday
17 | Who is bringing the Paan? | VM Yasmin | Completed | Badru bhai will deliver by 6:00pm
18 | Who is organizing Juice, Tea and Water | Captain Naz and Riaz Lalani | Completed | Lions Gate team will take care of that.
19 | Who is picking up Musicians/Singers from the Airport, what is the date/time of the pickup, where they supposed to be dropped off? | Major's and V. Majors | In-Process | Update 4/6/10: Confirmed from VM Yasmin, no pickup or drop-off services required by Neena to practice, sound check or at the event. Practice and sound check times are communicated to Neena by Bashir. Update 3/29/10: VM Yasmin will find out from Neena her plans after arriving to Vancouver, if she needs a ride from hotel to LG then Akbar Khoja has been assigned this task. Going back from practice to hotel, Bashir will be able to take care of that, also Bahsir will bring Neena for sound check and to the event. Captain Maa Naz will send Akbar the address of the hotel if pickup is needed. ------------------------------- Update 3/26/10 from VM Yasmin: Neena arriving Friday AM. Had a ride. Bashir will be there Friday 740 pm will rent a car. Notes from CC 3/24/10 : Majors and V. Majors will look after picking up the musicians from the airport. ------------------------------- Comments by Captain Maa Naz: one of the majors to pick up singers from the airport
20 | When and where is the band practice supposed to happen? Is it at Lions Gate JK? | Akbar Khoja | Completed | Update 3/27/10 from Akbar Khoja: I have now booked and confirmed the Lions Gate Al-Azhar room for band practice (Safar practice room) for friday April 9th from 8pm till midnight. Notes from CC 3/24/10 : Akbar Khoja will talk to Khalfaan and confirm if Friday is available at his warehouse. -------------------------------- Comments by Akbar Khoja: Friday at 9:00pm @ HQLG or talk to Khalfaan if it can be organized at his warehouse.
21 | Is Lions Gate social hall booked for practice? | Not assigned | Completed | Update 3/27/10 from Akbar Khoja: I have now booked and confirmed the Lions Gate Al-Azhar room for band practice (Safar practice room) for friday April 9th from 8pm till midnight. Fazzal Fatheali has arranged the sound with Adil for practice. Notes from CC 3/24/10 : HQLG is not available for Practice on Friday April 9th due to another event Friday night.
22 | What time is the sound check at Lions Gate JK? | Captain Maa Naz | In-Process | Update 3/27/10 from Akbar Khoja: Talked to Fazzal Fatheali who did communicated to Adil and the sound check will be at 2:30pm. Adil will start setting up at 1:00pm noon. Notes from CC 3/24/10 : Captain Maa Naz will talk to Adil regarding the time of the sound check. --------------------------------- Comments by Captain Maa Naz: Sound Check is on the day of the event (Saturday April 10th) @ 2:00pm
23 | Who is picking up Musicians/Singers from the hotel for sound check, who is dropping them back to the hotel, and bringing them back again for the show? | Major's and V. Majors | In-Process | Update 3/29/10: Bashir will be bringing Neena to the sound check and to the event from the hotel as Bashir will be renting a car. --------------------------------- Notes from CC 3/24/10 : Majors, V. Majors will assign one captain to take on this task and if not than Akbar Khoja will take care of this. --------------------------------- Comments by Captain Maa Naz: one of the majors to bring them for practice and back. One of the majors to bring them for sound check at 2p.m on Saturday. One of the majors to bring them back by 8p.m for the party.
24 | Food for Musicians Practice for Friday | Captain Maa Naz | In-Process | Update 4/5/10: Akbar will be picking up the food at 5:00pm from Safari. Update 3/29/10: Akbar will assign the task of picking up the food to Salma apa, food will be paid for at the time of pickup. --------------------------------- Update 3/27/10 from Captain Maa: Food for practice has been ordered from Safari (Pasta, Garlic bread and Salad) and Captain Maa has assigned Karim Fazzal to look into it. Notes from CC 3/24/10 : Captain Maa Naz will take care of ordering the food from Safari
25 | Who is arranging Sound System for Friday Practice day for musicians? | Captain Maa Naz | In-Process | Update 3/27/10: Fazzal Fatheali has communicated and confirmed with Adil to arrange the sound for Practice. Notes from CC 3/24/10 : If the practice is at warehouse the sound will be provided by Karim Fazzal, if at HQLG then Captain Maa will talk to Adil. --------------------------------- Comments by Captain Maa Naz: Practice sound will be arranged by Karim Fazal for Friday April 9th either at HQLG or Khalfaan's warehouse
26 | Are we selling Raffle tickets? | Major's and V. Majors | Completed | Notes from CC 3/24/10 : Major and V. Majors had decided that NO Raffle ticket will be organized for this event.
27 | Is the song list communicated to all the musicians? | VM Yasmin | In-Process | Update 3/30/10: VM Yasmin has requeted Bashir to re-send the song list to Salma Amlani, apprently it hasnt been communicated to the team yet by Karim Fazzal. -------------------------------- Update 3/27/10 from VM Yasmin: Bashir has provided the song list to Karim Fazzal. Notes from CC 3/24/10 : VM Yasmin will talk to Bashir on this topic
28 | When are the musicians arriving to Vancouver? | VM Yasmin | Completed | Update 3/27/10 from VM Yasmin: Neena arriving Friday AM. Had a ride. I will be there Friday 740 pm will rent a car. Notes from CC 3/24/10 : VM Yasmin will talk to Bashir on this topic
29 | Who is leading the band? | Akbar Khoja | In-Process | List of Musicians: Karim Fazzal - 778-990-7686 Abid Fazzal - 604-454-7561 Moiz Premji - 604-880-3933 Aku Hirji - 604-521-4838 Salma Amlani - 604-992-5000 Khalfan Kaba - 778-840-8401 Fahim Rawji - 778-881-6786 Bashir - 403-687-0001/ 403-607-0001 Neena Hardman - 403-542-3657 Salma (congo player) is the band lead and she will communicate to all band members regarding practice, sound checks, song lists, time to be at the event etc.
30 | Stage Decoration | VM Feroza | In-Process | VM Feroza is taking care of the stage decoration
31
32
33

## Tickets Distribution
# | JK Name | JK Captain's Name | JK Captain's ph# | Name and contact of Assigned Tkt Rep for this JK | # of Tkt's assigned to this JK | Amount owed by JK's
1 | IJKC Burnaby Darkhana | Nasir Govani | 604 - 291 - 7317 | Captain | 120 | 1200
2 | Burnaby Lake | Naz Rajani | 604 - 307 - 1569 | Captain | 150 | 1500
3 | Richmond | Alnoor Ladha | 604-760-4455 | Akber Dhanjee - 604-808-5478 | 78 | 780
4 | Head Quarters - Lions Gate | Nick Somani | 778 - 558 - 7866 | Captain | 96 | 960
5 | Fraser Valley | Yasmin Tejani | 604 - 575 - 8059 | Juby Vurren | 36 | 360
6 | Tri-City | Hannif Jinah | 604 - 351 - 5527 | Nasim Lalani - 778-285-0443 | 60 | 600
7 | Downtown | Hussein Nanji | 604 - 764 - 0605 | Captain | 48 | 480
8 | Abbortsford | Yasmin Keshavji | 1 - 604 - 852 - 8903 | Captain | 6 | 60
9 | Chilliwack | Aminmohammed Pirani | 1 - 604 - 793 - 0649 | Captain | 6 | 60
10 | M/K's Council Members | N/A | N/A | Mo/Zen 604-787-2070 | 50 | 500
| TOTAL Tickets |  |  |  | 650 | 6500